## Resource
Resource ID | Resource Name | Resource Type | Standard Rate | Overtime Rate | Accrual
R1 | Researcher | Work | $100.00/hr | $150.00/hr | Prorated
R2 | Literature review and tools | Material | 2000 | 0 | Prorated
R3 | Project Manager | Work | $75.00/hr | $112.50/hr | Prorated
R4 | Business Analyst | Work | $60.00/hr | $80.00/hr | Prorated
R5 | Blockchain Developer1 | Work | $125.00/hr | $185.00/hr | Prorated
R6 | Blockchain Developer2 | Work | $125.00/hr | $185.00/hr | Prorated
R7 | Developer3 | Work | $125.00/hr | $0.00/hr | Prorated
R8 | UI/UX Designer | Work | $50.00/hr | $75.00/hr | Prorated
R9 | Development tools & infra | Material | 10000 | 5 | Prorated
R10 | QA engineer | Work | $75.00/hr | $112.00/hr | Prorated
R11 | Testing Infrastructure | Material | 5000 | 5 | Prorated
R12 | DevOps Engineer | Work | $150.00/hr | $225.00/hr | Prorated
R13 | Cloud infrastructure | Material | 10000 | 5 | Prorated
R14 | Technical Support Specialist | Work | $50.00/hr | $75.00/hr | Prorated

## Cost
Task ID | Task Name | Resource IDs | Duration (weeks) | Cost/Week | Total Cost
T1 | Project Planning | R1 | 4 | 10000 | 40000
T2 | Requirements Gathering | R1, R3 | 6 | 20000 | 120000
T3 | System Design | R4, R5, R6 | 8 | 30000 | 240000
T4 | Development | R5, R6, R7 | 16 | 40000 | 640000
T5 | Testing | R10, R11 | 6 | 25000 | 150000
T6 | Deployment | R12 | 4 | 30000 | 120000
T7 | Training and Documentation | R3, R8 | 4 | 15000 | 60000
T8 | Maintenance and Support | R13, R14 | 52 | 10000 | 520000

## Summary
Phase | Cost
Project Planning | 40000
Requirements Gathering | 120000
System Design | 240000
Development | 640000
Testing | 150000
Deployment | 120000
Training and Documentation | 60000
Maintenance and Support | 520000
Total | 1890000